Item 7 - DRAFT IFSW Europe Workplan 2025-2027 V2

To be finalised after discussion on 5 October 2025

| Strategic theme | Action | Who | By When |
| --- | --- | --- | --- |
| - BUILDING STRONGER MEMBER ASSOCIATIONS Strategic aim: To support member associations to grow, support each other and achieve their objectives, in line with our common ethics and values. | - Implement the Strengthening Social Work and IFSW in Europe project Key elements: - Engage members through webinars, social media and other online platforms (e.g. padlets) - Trial new approaches to support and inclusion within 25/26. - Write up final report on approaches and implementation for adoption in DM 2026 - Develop and deliver webinars and other online meetings later in 2026 to disseminate, publicise and promote approaches and position of IFSWE in providing support and solidarity. - Commence evaluation of the project end 2026 Supporting members under duress - Develop more consistent processes and best practices for responding to calls for support, learning, intervention (etc) from members and engaging wider membership in mutual support and solidarity within the ‘Strengthening social work…’ project. | Led by Executive, Coordinator Jill Childs, involving members | Quarterly updates to IFSW Global Milestone report: DM 2026 |
| 2. INFLUENCING EUROPEAN AND NATIONAL SOCIAL WORK POLICIES Strategic aim: To influence and shape social work and social policies across Europe through promotion of our common ethics, values and knowledge through producing research, policy papers, webinars and other resources. | Responsive project - Plan future strategic direction for project outputs in management meeting of consortium leads end Oct 2025 Lisbon to include: - Agreeing development/ production/application of implementation tools and methods - Exploring options for funding for implementation through IFSW E and partners (through grant and/or commissioned implementation activities within services etc) - Developing networks of supporters/allies for Responsive approaches - Ensure use of all Responsive funding to achieve above aims by end January 2025 Cocoso project - Increase IFSW E executive visibility within and support to the project - Plan for involvement of IFSW E in delivering training and development inputs to candidates. Increasing policy impact of representatives/ regional commissioners - Work with representatives and regional commissioners on enhancing influencing skills and preparing and planning for webinars and learning activities over coming year | Ruth Allen Ana Radulescu Nicolai Paulsen Jill Childs Ruth Allen Ana Radulescu Herbert Paulischin John Brennan Ruth Allen Representatives | Project formal end – end February 2026 Ongoing (post-February) implementation and dissemination activities Ongoing Nov 2025 |
| 3. PROMOTING SOCIAL WORK PRACTICES AND IDENTITY Strategic aim: To celebrate, develop and defend social work practices and strengthening identity across Europe in alignment with our European and Global ethics, values and perspectives | - Disseminate outputs and learning from Responsive - Provide more social work practice and identity development opportunities/offers for social workers including with the input of the Representatives and Regional Commissioners - Appoint UN Regional Commissioner as soon as possible, in partnership with the Global UN Commissioner and IFSW Global, to sustain social work presence and impact in UN Geneva. - Reconvene the IFSW Europe Human Rights Network, build our focus on social work and human rights practice and set tangible actions/goals for the Network | Ruth Allen Ana Radulescu Nicolai Paulsen Jill Childs Ruth Allen Jill Childs Representatives Ruth Allen Priska Fleischlin Bernard Mayaka Enric Torras Kristine Evertz | From January 2025 – December 2026 Report to DM 2026 By Dec 2025 Nov 2025 |
| 4. SUPPORTING SOCIAL WORKERS’ WORKING CONDITIONS Strategic aim: To promote better working conditions, protection of rights at work and organisational practices that sustain the workforce. | - No concrete plans as yet - Initiating discussion on possible next steps at the DM in Oslo 2025 |  |  |
| 5. ADVOCATING FOR EUROPEAN SOCIAL WORK WITHIN EUROPEAN AND GLOBAL BODIES Strategic aim: To ensure social work perspectives and values have visibility and impact in key European institutions and systems, and ensure the voice of Europe is strong within IFSW Global. | - Provide one or two online skills and knowledge sessions in 2025/26 focused on ‘how to advocate successfully for social work and social workers and contribute effectively within European and Global institutions’ - Review how the Representatives Meeting time is structured and how the work of representatives feeds back to member associations and social workers across Europe. | John Brennan Ruth Allen Representatives and Regional Commissioners New Social Workers Network John Brennan Ruth Allen Representatives and Regional Commissioners New Social Workers Network | By March 2026 Proposal to DM 2026 |
| 6. LOBBYING AND CAMPAIGNING Strategic aim: To speak out and be widely recognized as the ethical voice of European social work and social workers on matters of professional, social and political importance. | - Develop and elucidate (write up) this strategic theme as cross cutting - Identify one or two specific priority campaign and lobbying activities for 2025/26 - Ensure motions passed at the DM are acted upon | Ruth Allen Executive group Executive group – following DM Executive Group | By end November 2025 By end November 2025 By end January 2025 and reported at DM 2026 |
| 7. IMPROVING INTERNAL AND EXTERNAL COMMUNICATIONS Strategic aim: To improve the regularity, impact and coherence of our communication and engagements activities amongst members and with our wider audiences. | An area for considerable development in the coming year and is high on the Executive’s priority list as timely, accessible communications are crucial for all our other projects. - Further develop content and dissemination of regular briefings for members and wider audience - by email, upload to the IFSW website and notification in IFSW bulletins - Increase use of on consolidated Facebook Account - Open IFSW Europe LinkedIn account if possible - Increase social media usage across all platforms, monitoring reach and impact - Use more online interactive tools to enable member engagement and networking with each other e.g. Padlet - Work with New Social Workers Group on best ways to reach new and younger social workers and fulfil the ambitions of the network | Executive Group with social media lead appointed New Social Workers group | Ongoing with report to next DM |
| 8. SECURING OUR FINANCES AND GROWTH Strategic aim: To manage and increase our financial resources and diversify our income to sustain our ability to support and develop social work and social workers in Europe. | - Through the Strengthening Social work and IFSW E project and other actions, promote benefits of IFSW E to social work associations across Europe, involving existing members, and seek to increase in paying membership. - Increase capacity to apply for funding and grants and increase other income generation through training interested members in grant and funding bids and creating a bidding and fund raising ‘virtual team’ / pool of capable and motivated members - Work specifically with the New Social Workers Network to build their capacity to gain funding | Executive group with active support of members Executive group with active support of members | Ongoing – report to DM 2025 Initial training session online by end Nov 2025 |
| 9. DELIVERING THE IFSW EUROPE CONFERENCE Strategic aim: To showcase and explore the work of IFSW and of European social work through high profile, bi-annual IFSW Europe conferences, engaging diverse social workers, experts by experience and other allies. | - Co-develop proposal to deliver the 2027 conference in Greece ( subject to vote in Oslo DM) - Put in place a clear model (contract) for delivery of the conference with risk and surplus share between the host association and IFSW - Promote the conference 2027 widely and consistently from 2026 onwards - Plan early for future conferences (2029 and beyond) | Proposed host/s Ruth Allen and Executive group Proposed host/s Ruth Allen and Executive group Executive group and all members Executive group and all members | Oct 2025 End Nov 2025 Ongoing Report to DM 2026 |
| 10. PLANNING FOR THE FUTURE AND SUPPORTING ALL GENERATIONS OF SOCIAL WORKERS Strategic aim: To support and enable the involvement of next generation social workers and innovations within IFSW E and across the profession | - Establish regular liaison between the New Social Worker Network (NSWN) and the Executive to support and facilitate delivery of their work plan 25/26 - Include the NSWN in the Representatives Meetings for feedback and ongoing information sharing. - Involve NSWN in ‘Strengthening Social Work…’ Project. - Use the members briefing and other IFSW E channels to disseminate updates about the NSWN. - Work with the NSWN to develop their bidding and grant application capacity as part of IFSW E’s overall capacity building. - Work with NSWN and the 2027 conference hosts to include NSW space/sub-conference and involve NSW in the conference development. - Actively encourage involvement of NSWs in Delegates’ Meetings through funding from associations and use of IFSW central subsidy budget. - Provide IFSW E budget of £3000.00 in 2026 for in person participation in relevant meetings/events. |  |  |