Item 7 - DRAFT IFSW Europe Workplan 2025-2027

To be finalised after discussion on 5 October 2025

| Strategic theme | Action | Who | By When |
| --- | --- | --- | --- |
| - BUILDING STRONGER MEMBER ASSOCIATIONS Strategic aim: To support member associations to grow, support each other and achieve their objectives, in line with our common ethics and values. | - Implement the Strengthening Social Work and IFSW in Europe project Key elements: - Trial new approaches to support and inclusion within 25/26. - Engage members through webinars, social media and other online platforms (e.g. padlets) - Write up final report on approaches and implementation for adoption in DM 2026 - Develop and deliver webinars and other online meetings later in 2026 to disseminate, publicise and promote approaches and position of IFSWE in providing support and solidarity. - Commence evaluation of the project end 2026 Supporting members under duress - Develop more consistent process and best practices for responding to calls for support, learning, intervention (etc) from members and engaging wider membership in mutual support and solidarity within the ‘Strengthening social work…’ project. | Led by Executive, Coordinator Jill Childs, involving diverse members | Quarterly updates to IFSW Global Milestone report: DM 2026 |
| 2. INFLUENCING EUROPEAN AND NATIONAL SOCIAL WORK POLICIES Strategic aim: To influence and shape social work and social policies across Europe through promotion of our common ethics, values and knowledge through producing research, policy papers, webinars and other resources. | Responsive project - Plan future strategic direction for project outputs in management meeting of consortium leads end Oct 2025 Lisbon to include: - Agreeing development and production of implementation tools and methods - Exploring options for funding for implementation (through grant and/or commissioned implementation activities within services etc) - Developing networks of supporters/allies for Responsive approaches - Using Responsive funding to achieve above aims by end January 2025 Cocoso project - Increase IFSW E executive visibility within and support to the project - Plan for involvement of IFSW E in delivering training and development inputs to candidates. Capacity building - Work with representatives and regional commissioners on preparing and planning for webinars and learning activities over coming year | Ruth Allen Ana Radulescu Nicolai Paulsen Jill Childs Ruth Allen Ana Radulescu Herbert Paulischin John Brennan Ruth Allen Representatives | Project formal end – end January 2026 Ongoing (post-January) implementation and dissemination activities Ongoing Nov 2025 |
| 3. PROMOTING SOCIAL WORK PRACTICES AND IDENTITY Strategic aim: To celebrate, develop and defend social work practices and strengthening identity across Europe in alignment with our European and Global ethics, values and perspectives | - Disseminate outputs and learning from Responsive - Explore possibility of producing more social work development opportunities/offers for our members including with the input of the Representatives and Regional Commissioners - Ensure appointment of UN Regional Commissioner as soon as possible, in partnership with the Global UN Commissioner and IFSW Global - Reconvene the IFSW Europe Human Rights Network and set some tangible actions/goals. | Ruth Allen Ana Radulescu Nicolai Paulsen Jill Childs Ruth Allen Jill Childs Representatives Ruth Allen Priska Fleischlin Bernard Mayaka Enric Torras Kristine Evertz | From January 2025 – December 2026 Report to DM 2026 By Dec 2025 Nov 2025 |
| 4. SUPPORTING SOCIAL WORKERS’ WORKING CONDITIONS Strategic aim: To promote better working conditions, protection of rights at work and organisational practices that sustain the workforce. | No concrete plans as yet but initiating discussion scheduled for the DM in Oslo 2025 out of which will come further plans. |  |  |
| 5. ADVOCATING FOR EUROPEAN SOCIAL WORK WITHIN EUROPEAN AND GLOBAL BODIES Strategic aim: To ensure social work perspectives and values have visibility and impact in key European institutions and systems, and ensure the voice of Europe is strong within IFSW Global. | - Provide one or two online skills and knowledge sessions in 2025/26 focused on ‘how to advocate successfully for social work and social workers and contribute effectively within European and Global institutions’ - Review how the Representatives Meeting time is structured and how the work of representatives feeds back to member associations and social workers across Europe. | John Brennan Ruth Allen Representatives and Regional Commissioners New Social Workers Network John Brennan Ruth Allen Representatives and Regional Commissioners New Social Workers Network | By March 2026 Proposal to DM 2026 |
| 6. LOBBYING AND CAMPAIGNING Strategic aim: To speak out and be widely recognized as the ethical voice of European social work and social workers on matters of professional, social and political importance. | - Develop and elucidate (write up) this strategic theme as cross cutting - Identify specific priority campaign and lobbying activities for 2025/26 - Ensure motions passed at the DM are acted upon | Ruth Allen Executive group Executive group – following DM Executive Group | By end November 2025 By end November 2025 By end January 2025 and reported at DM 2026 |
| 7. IMPROVING INTERNAL AND EXTERNAL COMMUNICATIONS Strategic aim: To improve the regularity, impact and coherence of our communication and engagements activities amongst members and with our wider audiences. | An area for considerable development in the coming year and is high on the Executive’s priority list as timely, accessible communications are crucial for all our other projects. - Further develop content and dissemination of regular briefings for members and wider audience - by email, upload to the IFSW website and notification in IFSW bulletins - Increase use of on consolidated Facebook Account - Open IFSW Europe LinkedIn account - Increase social media usage across all platforms, monitoring reach and impact - Use more online interactive tools to enable member engagement and networking with each other e.g. Padlet - Work with New Social Workers Group on best ways to each news and younger social workers | Executive Group with social media lead appointed New Social Workers group | Ongoing with report to next DM |
| 8. SECURING OUR FINANCES AND GROWTH Strategic aim: To manage and increase our financial resources and diversify our income to sustain our ability to support and develop social work and social workers in Europe. | - Through the Strengthening Social work and IFSW E project and other actions, promote benefits of IFSW E to social work associations across Europe, involving existing members, and seek to increase paying membership (income currently quite static at 30000 euros per year) - Increase capacity to apply for funding and grants and increase other income generation through training interested members in grant and funding bids and creating a bidding and fund raising ‘virtual team’. | Executive group with active support of members Executive group with active support of members | Ongoing – report to DM 2025 Initial training session online by end Nov 2025 |
| 9. DELIVERING THE IFSW EUROPE CONFERENCE Strategic aim: To showcase and explore the work of IFSW and of European social work through high profile, bi-annual IFSW Europe conferences, engaging diverse social workers, experts by experience and other allies. | - Co-develop bid with association/s to deliver the 2027 conference ( to be discussed and voted on in Oslo DM) - Put in place a clear model (contract) of risk and benefit share across the host association and IFSW - Promote the conference 2027 widely and consistently - Plan early for future conferences | Proposed host/s Ruth Allen and Executive group Proposed host/s Ruth Allen and Executive group Executive group and all members Executive group | Oct 2025 End Nov 2025 Ongoing Report to DM 2026 |
| 10. PLANNING FOR THE FUTURE AND SUPPORTING ALL GENERATIONS OF SOCIAL WORKERS Strategic aim: To support and enable the involvement of next generation social workers and innovations within IFSW E and across the profession | To be discussed with the NSW Network in their presentation to the 2025 DM in Oslo |  |  |